#### Team Structure

NICEHR Implementation Team:

- Sr. Program and Portfolio Manager: Develops the project plan, assigns tasks, and oversees timelines.

- Risk Manager: Identifies risks and creates mitigation strategies.

- Business Process Specialist: Optimizes, automates, and oversees workflows to improve efficiency and ensure compliance.

- Program Manager(s): Overall project oversight and stakeholder management.

- Clinical Analysts: Workflow assessment and requirements gathering. Supports UAT and validates clinical workflows.

- Implementation Consultants: Technical and operational support.

- Technical Specialists: Infrastructure assessment, planning and solution deliverables.

- Test Manager: Coordinates all testing activities and documents results.

- Cutover Lead: Coordinates and manages all activities related to cutover including any 3rd Party Vendors

- Data Migration Lead: Coordinates and manages all activities related to data migration including any 3rd Party Vendors

- Technical Implementation Consultant: Provides technical expertise during testing.

- Go-Live Coordinator: Manages go-live activities and troubleshooting.

- Support Staff: Provide on-site assistance to end-users, including via KLIKS™ support app.

- Training Coordinator: Develops training materials and conducts sessions.

- Change Management Specialist: Manages user engagement and communication.

- Trainers and Instructional Designers: Assist the Training Coordinator and work with stakeholders.

Healthcare Organization’s Core Team:

- Executive Leadership/Sponsors: Approves the project plan and allocates resources.

- Project Managers: Collaborate with the NICEHR Senior Portfolio Manager.

- Department Managers/Leaders: Provide operational input for planning, align departmental resources and change management.

- Clinical/Revenue Champions: Workflow expertise and staff liaison.  Provide feedback on system design and customization.

- IT Leadership: Technical coordination and system integration.  Validate technical feasibility.

- Integration Engineers and SMEs: Provide expertise for each module and legacy system.

- Super Users: Validate functionality and provide feedback.

- IT Specialists: Address technical issues during go-live.

- Clinical Champions: Offer peer support and resolve user issues.

- Executive Decision-Making Team: Handle escalations and critical decisions.

# Phase 1: Discovery and Needs Assessment

## Overview

The discovery phase forms the foundation of our implementation strategy. During this critical period, we work closely with your healthcare organization to understand existing workflows, identify pain points, and determine system requirements. This ensures our implementation aligns with both your organizational needs and healthcare industry standards.

## Implementation Steps

### 1. Stakeholder Engagement

Our first priority is meeting with key personnel across your organization. We'll schedule in-depth consultations with:

- Executive leadership team

- Clinical/Revenue Cycle staff representatives

- IT department leads

- SME’s

Key Activities:

- Structured interviews using our proven consultation framework.

- Documentation of current challenges and desired outcomes.

- Flexible scheduling to accommodate all workflows.

- Recording sessions (with permission) to ensure accurate capture of requirements.

Deliverables:

- Comprehensive stakeholder analysis report.

- Detailed meeting summaries with actionable items.

- Implementation roadmap based on stakeholder input.

Timeline: Weeks 1-3

- Initial scheduling and interviews (Week 1)

- Analysis and documentation (Week 2)

- Follow-up sessions as needed (Week 3)

### 2. Project Scope Definition

Working with your leadership team, we'll establish clear parameters for success:

Key Activities:

- Goal-setting workshops with key stakeholders.

- Development of measurable success metrics.

- Scope validation meetings.

- KPI framework development.

Deliverables:

- Formal project scope document.

- Success metrics and KPIs.

- Implementation timeline.

Timeline: Weeks 5-6

- Initial scope development (Week 5)

- Stakeholder finalization review and sign off (Week 6)

### 3. Workflow Analysis

We'll work alongside your team to map current processes and identify improvement opportunities:

Key Activities:

- Direct observation of all workflows.

- Department-specific process mapping.

- Identification of bottlenecks and inefficiencies.

- Collaboration with Clinical/Revenue Cycle Champions to validate findings.

Deliverables:

- Detailed workflow diagrams for each department.

- Comprehensive gap analysis.

- Prioritized list of process improvements.

Timeline: Weeks 2-4

- Process observation and mapping (Weeks 2-3)

- Analysis and documentation (Week 4)

### 4. Technical Infrastructure Review

Our technical team will conduct a thorough assessment of your current systems:

Key Activities:

- Network capacity evaluation.

- Hardware inventory and assessment.

- Software compatibility analysis.

- Performance testing.

- Environment analysis.

Deliverables:

- Infrastructure assessment report.

- Upgrade recommendations.

- Network optimization plan.

- Environment plan.

Timeline: Weeks 4-5

- Technical assessment (Week 4)

- Recommendations and planning (Week 5)

## Risk Management

Identifiable Risks and Mitigation Strategies:

- Resource Review

  - Risk: Understanding resource allocation and other projects that impact resources

  - Mitigation: Ensure alignment of all resources…(not sure what to write here)

- Schedule Management

  - Risk: Coordinating with busy clinical staff

  - Mitigation: Flexible scheduling options and backup meeting slots

- Communication

  - Risk: Information gaps between stakeholder groups

  - Mitigation: Regular status updates and clear documentation protocols

- Technical Integration

  - Risk: System compatibility issues

  - Mitigation: Early infrastructure assessment and proactive planning

- Data governance and management practices

  - Risk: Outdated processes and procedures

  - Mitigation: Ensure alignment with regulatory requirements, healthcare standards, and best practices.

### Phase 2: Project Planning

#### Overview

The project planning phase is critical for establishing a comprehensive roadmap for EHR implementation. This phase ensures that all stakeholders align on objectives, resources, timelines, and deliverables, setting a clear foundation for successful project execution.

#### Implementation Steps

1. Scope Definition (specific to the project plan)

Key Activities:

- Clearly outline project objectives and deliverables.

- Define project boundaries to prevent scope creep.

- Conduct collaborative workshops with stakeholders to ensure a shared understanding of project scope.

- Identify all known 3rd Party Vendors that will require either an integration and/or access to the EHR.

Deliverables:

- Formal scope document with objectives and deliverables.

- Clear boundaries and exclusions to manage expectations.

Timeline: Weeks 1-2

- Initial workshops and scope draft (Week 1)

- Stakeholder review, approve and sign off (Week 2)

2. Timeline and Milestones

Key Activities:

- Develop a realistic project timeline, breaking down tasks into manageable phases.

- Identify key milestones and deliverable dates.

- Ensure timelines allow for stakeholder reviews and feedback.

Deliverables:

- Detailed project timeline.

- Milestone chart with deliverable deadlines.

Timeline: Weeks 3-4

- Initial timeline drafting (Week 3)

- Stakeholder review and finalization (Week 4)

3. Resource Allocation

Key Activities:

- Identify required resources, including personnel, equipment, and budget.

- Develop a plan for optimal resource utilization.

- Validate resource availability with organizational leadership.

Deliverables:

- Resource allocation plan.

- Approved resource availability documentation.

Timeline: Weeks 5-6

- Resource identification and planning (Week 5)

- Validation and approval (Week 6)

4. Roles and Responsibilities

Key Activities:

- Assign specific roles and responsibilities to all team members.

- Create accountability frameworks for all project tasks.

- Communicate roles clearly across the organization.

Deliverables:

- Roles and responsibilities matrix.

- Accountability frameworks for project tasks.

Timeline: Weeks 7-8

- Role assignment and documentation (Week 7)

- Communication to stakeholders (Week 8)

5.  Communication Strategy

Key Activities:

- Establish communication protocols and governance structures.

- Define methods and frequency for stakeholder updates.

- Create templates for regular reporting and updates.

Deliverables:

- Communication plan with governance structure.

- Reporting templates and schedules.

Timeline: Weeks 8-9

- Draft communication plan (Week 8)

- Finalize and share with stakeholders (Week 9)

6. Risk Management Strategy- changed this to number 6 instead of 5

Key Activities:

- Conduct a comprehensive risk assessment.

- Identify potential challenges and develop mitigation strategies.

- Create contingency plans for unexpected scenarios.

Deliverables:

- Risk assessment report.

- Mitigation and contingency plan documentation.

Identifiable Risks and Mitigation Strategies:

- Scope Creep

  - Risk: Outdated processes and procedures

  - Mitigation: Ensure alignment with regulatory requirements, healthcare standards, and best practices.

- Data governance and management practices

  - Risk: Outdated processes and procedures

  - Mitigation: Ensure alignment with regulatory requirements, healthcare standards, and best practices.

- Resource Constraints

  - Risk: Insufficient availability of personnel or equipment.

  - Mitigation: Early resource planning and validation with leadership.

- Communication Breakdowns

  - Risk: Misalignment between teams and stakeholders.

  - Mitigation: Regular updates and structured communication protocols.

- Delays in Milestones

  - Risk: Failure to meet key deadlines.

  - Mitigation: Realistic timeline development with buffer periods and regular monitoring.

Timeline: Weeks 6-7

- Risk identification and mitigation planning (Week 6)

- Finalization and approval (Week 7)

### Phase 3: System Design and Customization

#### Overview

The system design and customization phase focuses on defining the EHR system’s features and tailoring it to meet the organization’s specific needs. This phase involves creating customized workflows, templates, and forms based on the outcomes of the needs assessment.

#### Implementation Steps

1. Collaborate with Stakeholders

Key Activities:

- Finalize system requirements in consultation with stakeholders.

- Ensure alignment with operational needs.

Deliverables:

- Approved system requirement documentation.

Timeline: Weeks 1-2

- Stakeholder consultations (Week 1)

- Requirement finalization (Week 2)

2. Review System Workflows, Templates, and Forms

Key Activities:

- Assess vendor-created workflows and templates.

- Identify required customizations and enhancements.

Deliverables:

- Customized workflows and templates.

Timeline: Weeks 3-4

- Workflow review (Week 3)

- Customization and approval (Week 4)

3. Design Clinical Decision Support Tools, Alerts, and Reports

Key Activities:

- Collaborate with clinical staff to define decision support tools.

- Develop alerts and reporting structures tailored to organizational needs.

Deliverables:

- Clinical/Revenue Cycle decision support tools.

- Alert and reporting framework.

Timeline: Weeks 5-6

- Tool and alert design (Week 5)

- Validation and testing (Week 6)

4. Department-Specific Workflow Development

Key Activities:

- Collaborate with each department and the EHR vendor to create customized workflows and tip sheets.

- Oversee department-specific development to ensure accuracy and usability.

Deliverables:

- Department-specific workflows and tip sheets.

Timeline: Weeks 6-8

- Initial development (Weeks 6-7)

- Review and finalization (Week 8)

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- Misalignment with Needs

  - Risk: System design may not fully meet organizational requirements.

  - Mitigation: Continuous collaboration with stakeholders and iterative reviews.

- Technical Feasibility Issues

  - Risk: Proposed designs may not align with existing infrastructure.

  - Mitigation: Early involvement of IT specialists to validate feasibility.

- User Resistance

  - Risk: Staff may resist new workflows or tools.

  - Mitigation: Engage Clinical/Revenue Cycle Champions to advocate for changes and provide training.

### Phase 4: Build Phase

#### Overview

The build phase focuses on constructing and configuring the components of the EHR system based on the customized design. This includes coding, system configuration, and the development of clinical features tailored to the organization’s workflows.

#### Implementation Steps

1. Configure the System

Key Activities:

- Align system configuration with the organization’s workflows.

- Validate configuration with stakeholder input.

Deliverables:

- Fully configured EHR system components.

Timeline: Weeks 1-2

- Initial configuration (Week 1)

- Validation and adjustments (Week 2)

2. Develop Custom Templates, Alerts, and Clinical Decision Support

Key Activities:

- Create custom templates for clinical/revenue and operational tasks.

- Develop alerts and decision support tools.

- Validate functionality with teams.

Deliverables:

- Custom templates and decision support tools.

- Alert system configuration.

Timeline: Weeks 3-4

- Development and testing (Week 3)

- Stakeholder review (Week 4)

3. Set Up User Roles, Permissions, and Access Levels

Key Activities:

- Define user roles and permissions based on job functions.

- Configure access levels to ensure data security and compliance.

Deliverables:

- User role and permission matrix.

- Configured access levels.

Timeline: Weeks 5-6

- Role definition and configuration (Week 5)

- Validation and updates (Week 6)

#### Risk Management

Identifiable Risk and Mitigation Strategies:

- Configuration Errors

  - Risk: Errors in system setup may disrupt workflows.

  - Mitigation: Iterative validation and testing during configuration.

- Feature Misalignment

  - Risk: Custom features may not meet user needs.

  - Mitigation: Continuous feedback from clinical teams during development.

- Access Control Issues

  - Risk: Improper access settings could lead to data breaches.

  - Mitigation: Rigorous testing of user roles and permissions.

### Phase 5: Data Migration Planning and Execution

#### Overview

The data migration planning and execution phase is essential for transferring data from legacy systems to the new EHR. This ensures data quality, accuracy, and usability while maintaining system integrity.

#### Implementation Steps

1. Develop a Data Migration Plan

Key Activities:

- Map data fields from legacy systems to the new EHR.

- Define a clear strategy for data extraction, transformation, and loading (ETL).

Deliverables:

- Comprehensive data migration plan.

Timeline: Weeks 1-2

- Initial mapping and strategy development (Week 1)

- Stakeholder review and approval (Week 2)

2. Extract, Clean, and Validate Data

Key Activities:

- Extract data from legacy systems.

- Clean and validate data to ensure quality and accuracy.

- Identify and resolve data discrepancies.

Deliverables:

- Cleaned and validated data set.

Timeline: Weeks 3-4

- Data extraction and cleaning (Week 3)

- Validation and discrepancy resolution (Week 4)

3. Test Data Migration

Key Activities:

- Conduct test migrations to ensure data accuracy and completeness.

- Validate migrated data against legacy data.

Deliverables:

- Test migration report.

- Validated data in the new EHR system.

Timeline: Weeks 5-6

- Test migration execution (Week 5)

- Validation and adjustments (Week 6)

4. Conduct Data Validation and Integrity Checks

Key Activities:

- Perform comprehensive integrity checks post-migration.

- Validate data accuracy with clinical and operational teams.

Deliverables:

- Post-migration validation report.

- Data integrity assurance.

Timeline: Weeks 7-8

- Integrity checks (Week 7)

- Final validation (Week 8)

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- Data Discrepancies

  - Risk: Inconsistent or incomplete data during migration.

  - Mitigation: Rigorous cleaning and validation processes.

- Technical Issues

  - Risk: Challenges in mapping legacy data to the new system.

  - Mitigation: Early involvement of IT specialists and iterative testing.

- Data Integrity Issues

  - Risk: Loss or corruption of data during migration.

  - Mitigation: Comprehensive validation and integrity checks post-migration.

### Phase 6: System Configuration and Integration

#### Overview

The system configuration and integration phase ensures that the EHR system is properly set up and seamlessly integrated with other systems, such as billing, laboratory, and imaging systems. This phase is critical for enabling efficient workflows and accurate data exchange across platforms.

#### Implementation Steps

1. Configure System Settings

Key Activities:

- Set up workflows and alerts in the system.

- Validate settings with stakeholders to ensure alignment with operational needs.

Deliverables:

- Fully configured system settings.

Timeline: Weeks 1-2

- Initial configuration (Week 1)

- Validation and adjustments (Week 2)

2. Integrate the EHR with Existing Systems

Key Activities:

- Establish interfaces with billing, laboratory, pharmacy, and imaging systems.

- Collaborate with module-specific experts to ensure seamless integration.

Deliverables:

- Integrated systems with validated interfaces.

Timeline: Weeks 3-4

- Integration setup (Week 3)

- Interface testing (Week 4)

3. Test Interfaces for Seamless Data Exchange

Key Activities:

- Conduct initial connectivity testing of system interfaces.

- Conduct end-to-end testing of system interfaces, and external devices (i.e. printers, scanners, tablets)

- Resolve any issues identified during testing.

Deliverables:

- Test reports and resolved issues.

Timeline: Weeks 5-6

- Testing execution (Week 5)

- Adjustments and validation (Week 6)

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- Integration Issues

  - Risk: Systems may not communicate effectively.

  - Mitigation: Rigorous testing and collaboration with module-specific experts.

- Configuration Errors

  - Risk: Incorrect settings may disrupt workflows.

  - Mitigation: Iterative validation and adjustments during configuration.

- Resource Gaps

  - Risk: Insufficient client-side resources for integration.

  - Mitigation: Ensure client team includes local experts with knowledge of legacy systems.

### Phase 7: Testing (Unit, System, and User Acceptance)

#### Overview

The testing phase ensures that the EHR system meets all functional requirements and user expectations. This phase includes unit testing, integrated testing, and user acceptance testing (UAT) to validate all components and workflows for clinical and revenue cycle.

#### Implementation Steps

1. Conduct Unit Testing

Key Activities:

- Test individual components of the EHR system.

- Identify and address any defects or inconsistencies.

Deliverables:

- Unit testing report with resolved issues.

Timeline: Weeks 1-2

- Initial unit testing (Week 1)

- Resolution of issues (Week 2)

2. Perform Integrated Testing

Key Activities:

- Test the system as a whole to ensure functionality and integration including any 3rd Party Vendor interfaces.

- Validate data flows across all interfaces.

Deliverables:

- System testing report with resolved issues.

Timeline: Weeks 3-4

- System testing execution (Week 3)

- Resolution of issues (Week 4)

3. Conduct User Acceptance Testing (UAT)

Key Activities:

- Provide training and validate system access to identified SMEs.

- Conduct UAT sessions with SMEs and Clinical/Revenue Cycle champions.

- Tailor vendor-provided test scripts to match the organization’s workflows.

- Gather feedback and implement required changes.

Deliverables:

- UAT report with user feedback.

- Approved workflows and configurations.

Timeline: Weeks 5-6

- UAT sessions (Week 5)

- Feedback analysis and adjustments (Week 6)

4. Conduct Regression and Volume Testing

Key Activities:

- Identify regression defects and resolve

- Ensure stability and performance

- Conduct volume testing

Timeline: Weeks 7-8

- Systems testing execution (Week 7)

- Resolution of issues (Week 8)

5. Conduct Technical Dress Rehearsal (TDR) Testing

Key Activities:

- Deploy, setup/configure and test all devices

- Resolve all issues

Timeline: Weeks 5-8

EHR Vendor:

- Vendor Representatives: Provide tailored test scripts and support testing activities.

4. Go/No-Go Decision Making

Key Activities:

- Evaluate system readiness for full-scale adoption.

- Convene an Executive Decision-Making Team to address escalations.

Deliverables:

- Decision documentation and action plan.

Timeline: Week 3

#### Decision-making and implementation.

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- Testing Delays

  - Risk: Insufficient time allocated for testing phases.

  - Mitigation: Develop a detailed testing schedule with buffer periods.

- Unresolved Issues

  - Risk: Critical issues may remain unresolved after testing.

  - Mitigation: Prioritize issues and allocate resources to address critical concerns.

- User Resistance

  - Risk: Users may be resistant to providing feedback or participating in UAT.

  - Mitigation: Engage Clinical and Revenue Cycle Champions to encourage participation and communicate the importance of feedback.

- 3rd Party Vendors Engagement

  - Risk: Lack of engagement to resolve issues

  - Mitigation: Escalate to stakeholders to manage vendor relationships

### Phase 8: Training and Change Management

#### Overview

The training and change management phase prepares users for the new EHR system through comprehensive training programs and effective change management strategies. This phase ensures smooth adoption and user satisfaction.

#### Implementation Steps

1. Develop Training Materials Tailored to User Roles

Key Activities:

- Create training manuals and materials based on vendor-provided vanilla resources.

- Tailor materials to specific user roles and workflows.

Deliverables:

- Role-specific training materials.

Timeline: Weeks 1-2

- Initial material development (Week 1)

- Tailoring and validation (Week 2)

2. Conduct Training Sessions for End-Users

Key Activities:

- Organize in-person and online training sessions.

- Provide hands-on practice with the system.

Deliverables:

- Training session reports.

- User competency assessments.

Timeline: Weeks 3-5

- Training execution (Weeks 3-4)

- Assessment and feedback (Week 5)

3. Conduct Login Labs for End-Users, Providers

Key Activities:

- Organize onsite sessions with End Users to confirm and validate system access

- Setup onsite sessions with providers to review system access and any customization

Timeline: Weeks 3-5

- Training execution (Weeks 3-4)

- Assessment and feedback (Week 5)

4. Implement Change Management Strategies

Key Activities:

- Set up an Executive Change Management Board (CAB) with stakeholders from the health system, NICEHR, and the vendor.

- Use KLIKS™ software to provide one-on-one support for physicians.

- Develop communication plans to engage users and address concerns.

Deliverables:

- Change management plan.

- CAB meeting minutes and action items.

- KLIKS™ utilization reports.

Timeline: Weeks 1-6

- CAB setup (Week 1)

- Ongoing engagement and support (Weeks 2-6)

5. Audit Project Work for Best Practices and Standards

Key Activities:

- Validate adherence to policies, procedures, and standards.

- Conduct regular audits and implement improvements.

Deliverables:

- Audit reports.

- Updated policies and procedures.

Timeline: Weeks 6-8

- Audit execution (Week 6)

- Recommendations and updates (Weeks 7-8)

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- User Resistance:

  - Risk: Resistance to new workflows and systems.

  - Mitigation: Provide role-specific training and one-on-one support through KLIKS™.

- Inadequate Training:

  - Risk: Insufficient training for end-users.

  - Mitigation: Offer multiple training formats and hands-on sessions.

- Communication Gaps:

  - Risk: Lack of engagement with users.

  - Mitigation: Establish clear communication plans and regular updates.

### Phase 9: Go-Live Preparation

#### Overview

The go-live preparation phase involves finalizing all aspects of the EHR implementation to ensure a seamless launch. This includes data migration, system backup, support planning, and readiness validation through comprehensive technical rehearsals and cutover planning.

#### Implementation Steps

1. Finalize Data Migration and Conduct Validation

Key Activities:

- Complete the final migration of data from legacy systems.

- Validate data accuracy and integrity to ensure readiness for go-live.

Deliverables:

- Data migration validation report.

- Finalized and migrated data set.

Timeline: Weeks 1-2

- Data migration (Week 1)

- Validation and issue resolution (Week 2)

2. Create a Support Plan for Go-Live

Key Activities:

- Develop on-site and remote support plans to address user issues during go-live.

- Assign support roles and responsibilities.

- Ensure 24/7 support availability for critical periods.

Deliverables:

- Comprehensive support plan.

- Assigned support team and contact list.

Timeline: Weeks 2-3

- Support plan development (Week 2)

- Team assignments and readiness (Week 3)

3. Conduct Final System Backup

Key Activities:

- Perform a complete backup of the system to secure data and configurations.

- Validate backup integrity and accessibility.

Deliverables:

- Backup validation report.

- Securely stored system backup.

Timeline: Week 3

- Backup execution and verification.

4. Create a Cutover Plan

Key Activities:

- Develop a detailed plan outlining the transition from legacy systems to the new EHR.

- Coordinate cutover activities with all stakeholders.

- Include contingency plans for unexpected issues.

Deliverables:

- Approved cutover plan.

- Cutover activity checklist.

Timeline: Weeks 3-4

- Cutover plan drafting (Week 3)

- Stakeholder review and approval (Week 4)

5. Conduct Technical Dress Rehearsal (TDR)

Key Activities:

- Simulate go-live scenarios to identify potential issues.

- Validate system functionality and readiness through mock workflows.

Deliverables:

- TDR report highlighting resolved and pending issues.

- Go-live readiness confirmation.

Timeline: Week 4

- Rehearsal execution and adjustments.

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- Data Migration Issues

  - Risk: Errors in final data migration may affect system functionality.

  - Mitigation: Rigorous validation and backup procedures.

- Support Gaps

  - Risk: Insufficient support resources during go-live.

  - Mitigation: Develop a robust support plan and assign clear roles.

- Technical Failures

  - Risk: System malfunctions during go-live.

  - Mitigation: Comprehensive technical rehearsals and contingency planning.

### Phase 10: Go-Live Execution

#### Overview

The go-live execution phase involves launching the EHR system in the live environment and providing robust support to address issues promptly. This phase ensures a smooth transition and continuous system performance monitoring.

#### Implementation Steps

1. Execute the Go-Live Plan

Key Activities:

- Transition from legacy systems to the new EHR.

- Implement the cutover plan developed in Phase 9.

Deliverables:

- Fully operational EHR system.

Timeline: Week 1

- Transition execution and monitoring.

2. Provide On-Site and Remote Support

Key Activities:

- Deploy support staff to assist end-users on-site.

- Utilize KLIKS™ support app for remote troubleshooting.

Deliverables:

- Support logs and issue resolution documentation.

Timeline: Weeks 1-2

- On-site and remote support activities.

3. Monitor System Performance and User Feedback

Key Activities:

- Track system performance metrics.

- Gather user feedback to identify improvement areas.

Deliverables:

- Performance monitoring report.

- User feedback summary.

Timeline: Weeks 2-3

- Monitoring and feedback analysis.

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- User Resistance

  - Risk: Users may face challenges adapting to the new system.

  - Mitigation: Provide on-demand support and training refreshers.

- Technical Issues

  - Risk: System errors or slow performance may occur.

  - Mitigation: Real-time issue tracking and immediate resolution by support teams.

- Escalation Delays

  - Risk: Delayed resolution of critical decisions.

  - Mitigation: Establish an Executive Decision-Making Team for rapid response.

### Phase 11: Post-Implementation Support and Optimization

#### Overview

The post-implementation support and optimization phase focuses on providing ongoing support, addressing issues, and optimizing the system to improve user satisfaction and system performance. This phase ensures the EHR continues to meet organizational needs over the long term.

#### Implementation Steps

1. Provide Post-Go-Live Support and Address Issues

Key Activities:

- Establish a dedicated support team to handle user inquiries and resolve issues.

- Monitor system usage to identify and rectify performance bottlenecks.

Deliverables:

- Resolved issue logs.

- Continuous support availability.

Timeline: Weeks 1-4

- Initial support deployment (Week 1).

- Issue resolution and follow-up (Weeks 2-4).

2. Gather User Feedback for System Optimization

Key Activities:

- Conduct surveys and interviews with end-users to collect feedback.

- Identify common challenges and areas for improvement.

Deliverables:

- User feedback reports.

- Prioritized optimization recommendations.

Timeline: Weeks 2-6

- Feedback collection (Weeks 2-4).

- Analysis and reporting (Weeks 5-6).

3. Conduct System Performance Reviews and Implement Improvements

Key Activities:

- Review system logs and performance metrics.

- Implement system updates and enhancements based on findings.

Deliverables:

- Performance review documentation.

- Updated and optimized system configurations.

Timeline: Weeks 6-8

- Performance review execution (Week 6).

- Implementation of improvements (Weeks 7-8).

4. Develop a Long-Term Maintenance Plan and Perform Regular Updates

Key Activities:

- Create a detailed plan for ongoing system maintenance.

- Schedule regular updates and training sessions for users.

Deliverables:

- Maintenance plan document.

- Scheduled updates and training sessions.

Timeline: Weeks 8-12

- Plan development and approval (Weeks 8-9).

- Initial updates and training sessions (Weeks 10-12).

#### Risk Management

Identifiable Risks and Mitigation Strategies:

- User Resistance to Changes

  - Risk: Users may be resistant to ongoing updates or optimizations.

  - Mitigation: Regularly communicate benefits of updates and provide additional training as needed.

- Maintenance Downtime

  - Risk: Maintenance activities may disrupt system availability.

  - Mitigation: Schedule maintenance during off-peak hours and notify users in advance.

- Insufficient Feedback Collection

  - Risk: Limited user feedback may result in suboptimal system adjustments.

  - Mitigation: Actively encourage user participation through multiple channels.