## End of Day Report
Baptist
NAME OF HOSPITAL
Team Lead Name : | Rafael Rodrigues |  | QUESTIONS TO ANSWER BELOW IN YOUR FREE TEXT ASSESSMENT
Date : | 2022-08-15 |  | 1. Where are the gaps?
2. What issues are you having? ( Include Ticket # )
3. Where are the areas where things are going well?
( PULSE ) Green = No Issues , Yellow = Some Issues or Red = Urgent
Location (indicate clinical location if different than main hospital) | Indicate shift (AM shift or PM shift) | PULSE | ASSESSMENT
ED |  | Closed | The stroke narrator does not include Cardene or Out of place orders. Was this intentional? Providers are struggling with reordering prescriptions after the patient has been discharged. They are working on the best workflow for this. INC0083528 Left without being seen needs to be added to the discharge disposition. INC083583 There is no consult for ED in Epic. Providers sometimes consult another ED. Some orders are not available at certain locations. When saving order sets if a med that is included in the order set is not available for the current location the provider must take extra steps to replace that order. Can this be changed? | "there is a built in formula that when you click on the dropdown box, depending what you select will turn the cell green, yellow or red) | the list is hidden so no one can change it
Ambulatory Site A1 |  | Urgent | CHALLENGES: Patient was registered under a wrong encounter and all the XR orders went to the wrong location that delayed a patient’s care. The issue was later taken care of. 1. INC: 0078640: End Users still don’t have an access to Delete/Edit wrong documents scanned in a patient’s chart under the Media Manager. 2. INC: 0069860: When trying to end LDCT lung CT exam we had a questionnaire add stop requesting to enter reconstructed image width on the exams. 3. inside MyChart: Patients are allowed to schedule themselves for an appointment which is not supposed to because it’s throwing off the front desk available schedule. 4. AdHoc note: for a trauma pt the note is going straight to the Pt. MyChart which is not suppose to.
Some Issues
|  | Closed | Closed
|  | Green | We have a float checking on them. Front desk is doing well. Provider has questions, but still doing okay.
Ambultory Site B1 |  | Some Issues | Provider was not in the clinic. Staff is getting better and better each day. They are still working on some clinical workflows
B2 |  | No Issues | Float checking on them. No major tickets or concerns.
B3 |  | Some Issues | Continuing to work with the providers setting up dot phrases, smart phrases. Also working on setting up preference lists.
B4 |  | No Issues | No support
B5 |  | Some Issues | The front desk is doing well. Few little glitches with insurance not verifying on some patients. Clinical staff are doing better. The providers still want some hand holding, but each day is getting better and better.
B6 |  | No Issues | They still have a few issues, but seem to be doing well. We have a float checking in with them.
B7 |  | Some Issues | Staff is doing a better. Front desk still waiting on role as both front desk have the role of Cadence but they do not have access to the same things. I do not have the ticket number for this.
B8 |  | Some Issues | See Oakleaf Primary Care
B9 |  | Some Issues | Today’s Focus: pre-charting, smarts sets, speed buttons, charge levels and scanning in immunizations.
B10 |  | Some Issues | The front desk is doing well. Few insurance questions and working in the workques. Clinical staff are doing good. The providers still want some hand holding, but each day is getting better.
B11 |  | Some Issues | Refill request that are coming from the pharmacy are still going to MA’s in baskets and MA’s are having to forward the RX request to the providers. Providers are receiving internal information from the Lab regarding the tube color information with no results in there in basket. INC 00830389 Refill request that are coming from the pharmacy are still going to MA’s in baskets
B22 |  | Some Issues | Today's Focus: E prescribe tickets was created today for Dr Meyers INC 0074226 and INC 0077432
B23 |  | Some Issues
B25 |  | Some Issues | Today's Focus: Follow up from previous week Check in and out Payments
B26 |  | Some Issues
B27 |  | Some Issues | Challenges: Creating order sets and and smartsets Today’s Wins: Helped a new provider create some smartsets and also note templates
B28 |  | Some Issues
B31 |  | Some Issues | Today’s focus: Ambulatory. Helping providers to navigate ProcDoc. Working through in basket Front desk. Helping with workflow.
B34 |  | Some Issues | Issues / Challenges -Anesthesiologists (Dr Quiggle) was not able to find GI Appointments on the Clay All Anesthesia Procedures Status Board Report to start the Anesthesia in the CLY OR 3 Procedure Room.. Patient was in the GI Procedure Room on the table. (Work around pull CLY GI patients from the OpTime Snapboard and add the CLY MAIN OR / CLY OR 3 to the Snapboard to pull all CLY ENDO Appointments) Snapboard had to configured to add in the appointment settings for the OSC at Clay. (CLY Main OR Cases shows on CLY ANES Status Board yet GI Appointments/Procedures does not) -Surgeon - Dr Knox (GI) was not able to see all of his patients from the Provider Schedule. Only 3 out of the 7 patients showed up as his scheduled was not configured to follow (CLY OR 3 ) Provider/Resources for Appointments) CLY GI Status Report is blank and none of the GI Appointments will show on tbd Status Report.- Surgeon - Dr Pizarro had issues with the Haiku after we did a new install of the Haiku Mobile App to her mobile phone .. Error - Physician Portal / Baptist ID was not syncing to confirm her username /password to use the Mobile app. After confirmation pin was sent and added twice log off log back in -Haiku was working after her second GYN Case. Nurse -PRE/PACU Navigators are missing from the PRE/PACU context / login. CLY OSC Nurses are not able to assign patients to the PRE/PACU beds. MUSE is not interfacing with Epic to send /transmit the EKGs to Epic after the
B35
B36
B37

## Sheet1 (hidden)
Pulse
No Issues | green
Some Issues | yellow
Urgent | red
Closed | grey