## Timeline (hidden)
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2025-01-01 | 2025-04-30 | 120 | Planning | 50 | 50
2025-04-15 | 2025-04-29 | 15 | Onboard Resources | 35 | 35
2025-05-01 | 2025-05-05 | 5 | Project Kickoff | 25 | 25
2025-05-01 | 2025-06-14 | 45 | Assessment | 15 | 15
2025-06-01 | 2025-08-29 | 90 | Discovery | 5 | 5
2025-08-01 | 2025-11-13 | 105 | Design & Build | 0 | 0
2025-11-01 | 2025-11-30 | 30 | EUAT | -10 | -10
2025-12-01 | 2026-02-28 | 90 | Intergrated Testing | -15 | -15
2026-01-01 | 2026-05-30 | 150 | Hardware | -20 | -20
2026-04-01 | 2026-05-15 | 45 | Training | -35 | -35
2026-05-01 | 2026-05-30 | 30 | Dry Run | -45 | -45
2026-05-01 | 2026-05-01 | 1 | Scheduleing Go-Live | -50 | -50
2026-06-12 | 2026-06-12 | 1 | Cut Over | -60 | -60
2026-07-01 | 2026-07-01 | 1 | Go-Live | -70 | -70
2026-08-01 | 2026-08-01 | 1 | Support | -80 | -80
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2025-01-01 |  |  | Start, Jan 1 | 50
2025-04-01 |  |  | April #1 | 50
2025-07-01 |  |  | July #2 | 50
2025-10-01 |  |  | Oct #3 | 50
2026-01-01 |  |  | Go-Live | 50
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1

## Project Plan
Task ID | Task Name | Notes: | Owner | Number of Days to complete | Start Date (prior to golive) | Finish(prior to golive) | % Work Completed | Tools | Status
Phase I- Discovery and Needs Assessment
| Stakeholder Kick-off Meeting | Schedule a meeting with stakeholders | Nicergroup/Stakeholders | 1 Day
| Define Project Charter |  | Nicergroup/Stakeholders | 3 weeks |  |  |  | Project Charter
| Define Project Scope | Develop project scope and |  | 6 weeks
| Identify Workflows | Document workflows across each department. | Nicergroup/Clinical Champions/IT | 6 weeks
| Assess Technology Infrastructure | Conduct assessment of current IT infrastructure | Nicergroup/IT | 6 weeks
PLANNING
| Project Kick-off Meeting |  | Nicergroup | 1 week
Assign Project Team and Roles and Responsibilities
| Create Project Plan for client meetings |  |  | 5 Days
| Create Teams Folder Template | See Team tab |  | 1 Day
DISCOVERY
| Client Projections | Use Staffing Prep Worksheet- send prior to walk through to client if possible. Otherwise complete it while on site | PM | 14 Days | 120 Days | 90 Days
| Create and send the Nicergroup Staffing Assessment | [6 empty] | Nicergroup Staffing Assessment
| Schedule walk-through | decide who should be attending this walk-through | PM/Client
Attend the walk-through
| Review and discuss Nicergroup Staffing Assessment | This may be an ongoing process until you are able to get each department, application, and headcount established
| Complete the Nicergroup Needs Assessment | Combine data from staffing assessment into Needs Assessment- this breaks out each module used for the go-live | PM |  |  |  |  | Nicergroup Needs Assessment
| Schedule Assessment meeting | review the numbers and get approval from the client. This process can be reviewed through the life cycle up until day of go-live | [5 empty] | Nicergroup Needs Assessment
| Send approved project scope to Sales for SOW | this would be if we don't do a walk-through and client is telling us what their needs are. |  | 1 Day | 120 Days | 90 Days
| Create and complete template for resources needed | once SOW signed (subject to change) this contains the "ASK" (skill matrix) | PM | 1 Day | 120 Days | 90 Days |  | Skillmarket Release
PREPARATION WORK
| Schedule creation | Dependent on Staffing Assement approval Work with Client to obtain any outstanding location hours | PM | 90 Days | 90 Days | 2 Days
| Export scheduling template | Use Connecteam schedule export Add users, job type, location etc | PM |  |  |  |  | Connecteam
| Candidate Notification |  |  | 90 Days | 90 Days | 5 Days
| Create Candidate template |  | PM
| Assign Candidates | Assign candidates to a specific module, this should correlate with the staffing assessement "ask". Select staff to meet client need. Add backups (20%). Deliniate for onboarding who is active roster vs. backups | PM
| Submit Candidates to onboarding team | send the template to onboarding | PM |  |  |  |  | Nicergroup Needs Assessment
| Onboarding of Resources |  | Onboarding |  | 90 Days | 5 Days
Receives ATE candidates from PM
| Verifies compliance with client | onboarding confirms that we have the client compliance (ideally this is done before offers go out, because if not- it’s blank for the ATE and causes confusion)
| Sends out offer letters | Offers are sent to those on the roster | Onboarding
| Tracks Roster status and Compliance | After three days all non responsive candidates are dropped
| Candidate Acceptance | Onboarding initiates Compliance by communicating requirements to ATE | Candidate
| Candidate Monitoring |  | PM and Onboarding
| Internal Processes |  | ALL Nicergroup Teams | 5 Days | 90 Days | 60 Days
| Review signed SOW | Upon receiving the fully executed SOW, confirms that the dates have not changed from the original release and what is in the SOW | ALL |  |  |  |  | SOW
| Setup Project Email (alias email) | PM requests from IT: Need e-mail project aliases for Logistics (Deconess Logistics) ATE will use these to notify apppropriate owners of issues | PM |  |  |  |  | Email
| Set up meeting with Logistics | Begin discussion with logistics to identify airport to use, hotels, ground transportation strategy (cars, shuttles) | PM/Logistics
| Send site summary to logistics for hotel and logistics planning. | Should also include the strategy and needs for an onsite orientaiton if it applies. | PM |  |  |  |  | Nicergroup Needs Assessment
| Create site map | google maps- showing hotels and locations of sites | Logistics |  |  |  |  | Google Maps
| Solidify Ground transportation strategy | Transportation from airport Solidify cars/shuttle contracts | Logistics
| Solidify Transportation Contracts |  | Logistics
| Solidify Hotel Contracts | "This will be dependent on support numbers required and support locations (if multiple and/or widespread) Consideration of carpools/shuttles" | Logistics
| Confirm Orientation Location/Dates | this is discussed during client planning sessions. Nicergroup hosting a location or client hosting a location. Plan for large groups | PM/Client
| Onboarding sends ATE info on Concur and ADP | Onboarding is responsible for informing the ATE on the use of ADP and Concur once ATE is Compliant and ready for travel | Onboarding
| Send Book your Flight | Timing for this varies, but want this to occur in a timely manner relative to Go Live to minimize cost | Onboarding
| Orientation Preparation |  | PM | 2 Days | 4 days | 2 Days
| Update slide deck | Add Orientation information. Update 3 Slide onsite leadership | [5 empty] | Nicergroup Project Orientation ppt
| Create /Send orientation invites from the client | Client responsible for sending out Invites to their staff if it is their Invite | Client/PM
| Orientation Invites to ATEs | Nicergroup will then forward this invite to ATE if virtual | PM
| Connecteam Setup |  | Scheduling Manager | 2 Days | 5 Days | 5 Days
| Set up meeting with PM for Connecteam | Review project dynamics/set up Connecteam | PM/Scheduling Manager
| Create Project | see Connecteam tab | Scheduling Manager
| Project Set Up | see Connecteam tab | Scheduling Manager |  |  |  |  | Connecteam
| Set up Nicergroup Documents | see Connecteam tab | PM |  |  |  |  | Connecteam
| Set up Forms | see Connecteam tab | PM |  |  |  |  | Connecteam
| Set up Chat | see Connecteam tab | PM |  |  |  |  | Connecteam
| Send ATE Welcome | email/slidedeck/connecteam slidedeck | PM |  | 5 Days | 5 Days
| Import Users |  | Scheduling Manager |  | 4 Days | 3 Days |  | Connecteam
| Logistics email sent | This will include information about shuttles to hotel, shuttles to Orientation, hotel that they are assigned to | Logistics |  | 3 Days | 2 Days
| APM Email (Onsite Leadership) | PM creates the template for the APM. This must be sent from the Nicergroup email of the APM. | APM |  | 1 Day | 1 Day
| Start Badge process | ATE sending in photo to create badge see badge process | Scheduleing Manager/Jill |  | 5 Days | 5 Days
| Ship Laptops/Badges/Vest | Onsite Leadership (APM/ZL/POC) will use | PM/IT
EXECUTION
| Travel Day |  | PM/APM/Logistics |  | Go-Live | NA
Monitor Candiates arriving
| Onsite Arrival |  | PM/Team members
| Client Meet and Greet | PM/APM/ZL and others as needed to meet with client and staff managers to review the lay of the land
| Hotel Check-in | Meet and Greet your Onsite Leadership team
| Orientation Check-In | Day of Orientation
| Onsite Orientation Presentation | PM presents Nicergroup information Provide Nicergroup standard content. Client will provide interal content and staffing for the breakout sessions.
| Virtual Orientation Presentation | PM presents Nicergroup information
| Airtable Backup removal |  | Onboarding |  | 3 Days After Go-Live
During the Go-Live
| Attendance Form (arrival & departure forms) | Daily and reviewed by APM and Zone Leads | PM
| Cutover team supports the golive Effort | We usually go in one hour before cutover to assist with downtime prep. When the sytem comes up our team is in place to begin support. | ATE/ PM/APM
| PM is present at Cutover for oversight | We are present virtually or onsite to insure all staff are accounted for, Shuttles schedules are being executed properly, team has full coverage. | PM/ Onsite Leaders
| Connecteam: During Go Live | see Connecteam tab | Scheduling Manager
OnSite Reporting
| End of Day Report | Nicergroup leaders collect this data through forms. The data is agregated to provide project adoption insight to the client leadership and make decision on staffing model updates and taper consideration | PM/Onsite Leadership
| Chart end of day report | Prepare to share with the client.
| Managers reports | Help to gauge staff adoption. These metrics are used to gauge adoption from the client view. This is very helpful for taper discussions. | PM/Onsite Leadership
| Time Sheets/Burn Report | Need to work with Misty to review time sheets | Scheduling Manager/PM/APM / Payroll
| Send Client Burn Report | send out 3 days after the 1st week | PM/Client
| Set Taper Dicussion Meeting with client | Make sure client gets the appropriate Stakeholders
| Client Budget reductions | Staff tapers according to original plan- this can and should be adapted to project and success.
| Execute first taper | Based on a collaborative effort with the client a taper model is agreed upon. Using Airtable to faciliate the taper the PM will select the team member to be tapered. Emails go out to the affected staff. Logistics determines airport transportation methods and communicates that to the staff. | PM/ Logistics |  | The goal is to execute the taper at least 48 before travel.
| Execute second taper | Based on a collaborative effort with the client a taper model is agreed upon. Using Airtable to faciliate the taper the PM will select the team member to be tapered. Emails go out to the affected staff. Logistics determines airport transportation methods and communicates that to the staff. | PM/ Logistics
| Execute final taper | Based on a collaborative effort with the client a taper model is agreed upon. Using Airtable to faciliate the taper the PM will select the team member to be tapered. Emails go out to the affected staff. Logistics determines airport transportation methods and communicates that to the staff. | PM/ Logistics
Discuss Extension beyond scope
CLOSE OUT
| Archive Airtable |  | PM |  | Post Go-Live | 10 Day Post Go-Live
| Archive Team Document Folder |  | PM |  | Post Go-Live | 10 Day Post Go-Live
| Export Evaluations and update SKM |  | PM |  | Post Go-Live | 10 Day Post Go-Live
| Archive Connecteam Chats and Forms |  | PM/ Onsite Leaders/ Client |  | Post Go-Live | 10 Day Post Go-Live
| Validate ADP/Connect hours sync |  | Scheduling PM / Payroll |  | Post Go-Live | 10 Day Post Go-Live
| Connecteam: Post Go Live |  | Scheduling Manager |  | Post Go-Live | 10 Day Post Go-Live
| Archive teams folder |  | PM |  | Post Go-Live | 10 Day Post Go-Live
| Remove User seats |  | Connecteam Owner |  | Post Go-Live | 10 Day Post Go-Live
| Finalize Burn Report |  | PM/Client |  | Post Go-Live | 10 Day Post Go-Live

## Project TL
|  | Project Management |  |  |  | Ops |  |  |  | IT
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | Jul | Aug | Start | End | Duration | Task
Phase 1
[21 empty] | 2025-01-01 | 2025-04-30 | 120 | Phase 1
[21 empty] | 2025-01-02 | 2025-01-02 | 1 | Stakeholder Kick-off
[21 empty] | 2025-01-01 | 2025-02-14 | 45 | Assessment
[21 empty] | 2024-02-14 | 2024-03-29 | 45 | Technology Review
[21 empty] | 2024-04-01 | 2024-05-15 | 45 | Discovery
[21 empty] | 2025-06-01 | 2025-08-29 | 90 | Phase 2
[21 empty] | 2025-08-01 | 2025-11-13 | 105 | Project Kick-off
[21 empty] | 2025-11-01 | 2025-11-30 | 30 | Harware
[21 empty] | 2025-12-01 | 2026-02-28 | 90 | Testing
[21 empty] | 2026-01-01 | 2026-05-30 | 150 | Hardware
[21 empty] | 2026-04-01 | 2026-05-15 | 45 | Training
[21 empty] | 2026-05-01 | 2026-05-15 | 15 | TDR
[21 empty] | 2026-06-12 | 2026-06-12 | 1 | Cut Over
[21 empty] | 2026-07-01 | 2026-07-01 | 1 | Go-Live
[21 empty] | 2026-08-01 | 2026-08-01 | 1 | Post Implementation
[17 empty] | Cutover |  |  |  | add TDR
Go-Live
Post Implementation
Formulas:
End = [Start]+[Duration]-1

## Detailed Timeline
|  | Project Management |  |  |  | Ops |  |  |  | IT
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov |  | Dec | Jan |  | Feb | Mar | Apr |  | May | Jun |  | Jul | Aug | Start | End | Duration | Task
Planning
|  |  | Onboard Resources | [20 empty] | 2025-01-01 | 2025-04-30 | 120 | Planning
|  |  |  | Program Kick-Off | [19 empty] | 2025-04-15 | 2025-04-29 | 15 | Onboard Resources
[24 empty] | 2025-05-01 | 2025-05-05 | 5 | Project Kickoff
|  |  |  | Assessment | [19 empty] | 2025-05-01 | 2025-06-14 | 45 | Assessment
[24 empty] | 2025-06-01 | 2025-08-29 | 90 | Discovery
[5 empty] | Discovery | [18 empty] | 2025-08-01 | 2025-11-13 | 105 | Design & Build
[24 empty] | 2025-11-01 | 2025-11-30 | 30 | EUAT
[7 empty] | Design & Build | [16 empty] | 2025-12-01 | 2026-02-28 | 90 | Intergrated Testing
[24 empty] | 2026-01-01 | 2026-05-30 | 150 | Hardware
[10 empty] | EUAT | [13 empty] | 2026-04-01 | 2026-05-15 | 45 | Training
[24 empty] | 2026-05-01 | 2026-05-15 | 15 | TDR
[11 empty] | Integrated Testing | [12 empty] | 2026-06-12 | 2026-06-12 | 1 | Cut Over
[24 empty] | 2026-07-01 | 2026-07-01 | 1 | Go-Live
[14 empty] | Hardware | [9 empty] | 2026-08-01 | 2026-08-01 | 1 | Support
Training
[19 empty] | TDR |  |  |  |  | add TDR
Cutover
GOLIVE
Support
Formulas:
End = [Start]+[Duration]-1

## Sheet1
2025-04-15 | 2025-04-29 | 15 | Onboard Resources Apr 15 - Apr 29 | 45 | #REF!
2025-05-01 | 2025-05-05 | 5 | Project Kickoff May 1 - May 5 | 40 | -5
2025-05-01 | 2025-06-14 | 45 | Assessment May 1 - Jun 14 | 35 | 35
2025-06-01 | 2025-08-29 | 90 | Discovery Jun 1 - Aug 29 | 30 | 30
2025-08-01 | 2025-11-13 | 105 | Design & Build Aug 1 - Nov 13 | 25 | -5
2025-11-01 | 2025-11-30 | 30 | EUAT Nov 1 - Nov 30 | 20 | 20
2025-12-01 | 2026-02-28 | 90 | Intergrated Testing Dec 1 - Feb 28 | 15 | -5
2026-01-01 | 2026-05-30 | 150 | Hardware Jan 1 - May 30 | 10 | -5
2026-04-01 | 2026-05-15 | 45 | Training Apr 1 - May 15 | -5 | -15
2026-05-01 | 2026-05-30 | 30 | Dry Run May 1 - May 30 | -10 | -5
2026-05-01 | 2026-05-01 | 1 | Scheduleing Go-Live May 1 - May 1 | -15 | -5
2026-06-12 | 2026-06-12 | 1 | Cut Over Jun 12 - Jun 12 | -20 | -5
2026-07-01 | 2026-07-01 | 1 | Go-Live Jul 1 - Jul 1 | -25 | -5
2026-08-01 | 2026-08-01 | 1 | Support Aug 1 - Aug 1 | -30 | -5

## About (hidden)
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.