## High Level Delivery Plan
TNG - Modules and Apps ( Web and Mobile)
No# | Module / Applications | Submodule | Feature List | Milestone | Effort [Min] in Months | Effort [Max] in Months | Comments
| Detail Analysis and Architecture |  |  | 1 | 2 | 2.5 | These two phases will be done in parallel to development of all Modules
Design Phase ( Web and Mobile)
1 | Consultant Onboarding | On Boarding process | Onboarding Invitation Dispatching | 2 | 2 | 3
User basic Information and Document Collection
Consultant Availability Schedule Management
Documentation Verification and Registration completion
|  | Service request and agreement process | Receive Service request
Match making with available consultants
Consultant consent and Agreement
|  | Document/agreement monitoring | Document/agreement timeline monitoring
Dispatch notification for renewals
Renewals monitoring and conformation
2 | Connect | Enterprise Intranet | Invitations | 3 | 2 | 3
Dashboard
Feeds
Groups
Tasks
Manual and Files
Townhall meeting managment
Event schedular via Calander
|  | Consultant Intranet | Same Features as above mentiod in Enterprise Intranet
3 | Communication/Chatting | Chat | Chats | 4 | 2 | 2.5
Contacts list
Channels
History
Files
Calender
Notes
4 | Schedule Management & Time Managment | Time managment | Track labour cost using live update in time sheet. | 5 | 2.5 | 3
Pay roll managment and payroll export
|  | Scheduling | Prepare Employees Shift schedule
Re-shedule Shifts
Shift Reminders and Notifications
5 | Attendance/time management (Cloud base clocking system) | Check in / Check out | Geo fancing and IP based permission for Check in /Checko ut
Timesheet with graph representation
Payroll managment
Clous base clocking system (Data storage on the cloud)
6 | Task management (Service management) | Task Managment | DashBoard (Detail visualization of requests with their status) | 6 | 2 | 2.5
Task Scheduler
Curtomer request status as per process like (Done, pending, overdue or On hold)
| Traning Managment | Knowledge base | A collaborative editing and sharing Module. While working on SOPs, documenting polices and article writing. | 7 | 1.5 | 2
7
|  | Online LMS (Learning Management System) | A complete multimedia traning with assesment and reporting tools.
8 | Data collection and analysis | Online form builder | Dynamic Report Builder which is based on multiple parameters and notifications.Notifications will be send via SMS / Emails and Chats | 8 | 1.5 | 2
Instant Notifications on data updation
View, export and analyze data
|  |  |  | Total | 15.5 | 20.5
Note: | UI/UX for Web and Mobile | Zoho design is benchmark
Data Security will be HIPPA compliance